## Right_of_Minzhu_Road
Measured Deflection Value Record Sheet Road Inspection Form - 01
Project Name: Starting and Ending Pile Number: Right Side To Inspection Date: 2010.4.30
Contractor: Liaoyang Highway Asphalt Mixing Plant Sub-item Project Name: Original Pavement Layer
Design Resilient Modulus L(BZZ-100)(0.01mm) |  |  |  |  | Test Vehicle Model | FALING CA10B |  | Vehicle type coefficient K4 |  | 1.6
Rear axle load/tire pressure (KN/MPa):
Seasonal coefficient K1 | 1.25 |  | Temperature coefficient K3 |  |  | L = L / K1 × K3 × K4
(0.01mm)
Pile Number (Left Side) | Reading |  | Deflection |  | Remarks | Pile Number (Right Section) | Reading |  | Deflection |  | Remarks
| Left | Right | Left | Right |  |  | Left | Right | Left | Right
K0+000 | 21 | 12 | 42 | 24 |  | K1+600 | 15 | 12 | 30 | 24
K0+050 | 35 | 37 | 70 | 74 |  | K1+650 | 14 | 8 | 28 | 16
K0+100 | 16 | 7 | 32 | 14 |  | K1+700 | 16 | 13 | 32 | 26
K0+150 | 12 | 13 | 24 | 26 |  | K2+000 | 11 | 15 | 22 | 30
K0+200 | 20 | 15 | 40 | 30 |  | K2+050 | 2 | 3 | 4 | 6
K0+250 | 18 | 17 | 36 | 34 |  | K2+100 | 3 | 20 | 6 | 40
K0+300 | 29 | 30 | 58 | 60 |  | K2+150 | 29 | 17 | 58 | 34
K0+350 | 22 | 20 | 44 | 40 |  | K2+200 | 19 | 20 | 38 | 40
K0+400 | 21 | 21 | 42 | 42 |  | K2+250 | 21 | 11 | 42 | 22
K0+450 | 21 | 20 | 42 | 40 |  | K2+300 | 9 | 5 | 18 | 10
K0+500 | 13 | 12 | 26 | 24 |  | K2+350 | 17 | 9 | 34 | 18
K0+550 | 16 | 20 | 32 | 40 |  | K2+400 | 23 | 10 | 46 | 20
K0+600 | 31 | 15 | 62 | 30 |  | K2+450 | 22 | 25 | 44 | 50
K0+650 | 32 | 19 | 64 | 38 |  | K2+500 | 12 | 10 | 24 | 20
K0+700 | 28 | 27 | 56 | 54 |  | K2+550 | 18 | 18 | 36 | 36
K0+750 | 32 | 15 | 64 | 30 |  | K2+600 | 23 | 16 | 46 | 32
K0+800 | 14 | 15 | 28 | 30 |  | K2+650 | 26 | 20 | 52 | 40
K0+850 | 13 | 10 | 26 | 20 |  | K2+700 | 15 | 14 | 30 | 28
K0+900 | 17 | 16 | 34 | 32 |  | K2+750 | 10 | 22 | 20 | 44
K0+950 | 20 | 21 | 40 | 42 |  | K2+800 | 9 | 15 | 18 | 30
K1+000 | 31 | 23 | 62 | 46 |  | K2+850 | 29 | 14 | 58 | 28
K1+050 | 3 | 19 | 6 | 38 |  | K2+900 | 23 | 27 | 46 | 54
K1+100 | 22 | 20 | 44 | 40
K1+150 | 8 | 11 | 16 | 22
K1+200 | 11 | 14 | 22 | 28
K1+250 | 11 | 17 | 22 | 34
K1+300 | 5 | 18 | 10 | 36
K1+350 | 11 | 20 | 22 | 40
K1+400 | 14 | 6 | 28 | 12
K1+450 | 14 | 12 | 28 | 24
K1+500 | 21 | 26 | 42 | 52
K1+550 | 6 | 17 | 12 | 34
L | 34.1296 | S | 14.5955 | Za | 2 | Lr=L+ZaS | 63.3207 |  | Actual Score | 100
Technical Supervisor: Quality Inspector: Recorder:

## Left_of_Minzhu_Road
Measured Deflection Value Record Sheet Road Inspection Form - 01
Project Name: Minzhu Road Project Starting and Ending Pile Numbers: Left side from k0+000 to k3+000 Inspection Date: 2010.4.30.
Contractor: Liaoyang Highway Asphalt Mixing Plant Sub-item Project Name: Original Pavement Layer
Design Resilient Modulus L(BZZ-100)(0.01mm) |  |  |  |  | Test Vehicle Model | FALING CA10B |  | Vehicle type coefficient K4 |  | 1.6
Rear axle load/tire pressure (KN/MPa):
Seasonal coefficient K1 | 1.25 |  | Temperature coefficient K3 |  |  | L = L / K1 × K3 × K4
(0.01mm)
Pile Number (Left Side) | Reading |  | Deflection |  | Remarks | Pile Number (Right Section) | Reading |  | Deflection |  | Remarks
| Left | Right | Left | Right |  |  | Left | Right | Left | Right
K0+000 | 22 | 15 | 44 | 30 |  | K1+600 | 12 | 15 | 24 | 30
K0+050 | 14 | 16 | 28 | 32 |  | K1+650 | 13 | 25 | 26 | 50
K0+100 | 24 | 22 | 48 | 44 |  | K1+700 | 14 | 18 | 28 | 36
K0+150 | 24 | 20 | 48 | 40 |  | K1+975 | 16 | 13 | 32 | 26
K0+200 | 24 | 22 | 48 | 44 |  | K2+025 | 17 | 15 | 34 | 30
K0+250 | 20 | 21 | 40 | 42 |  | K2+075 | 13 | 10 | 26 | 20
K0+300 | 10 | 13 | 20 | 26 |  | K2+125 | 10 | 30 | 20 | 60
K0+350 | 24 | 12 | 48 | 24 |  | K2+175 | 10 | 14 | 20 | 28
K0+400 | 9 | 10 | 18 | 20 |  | K2+225 | 16 | 14 | 32 | 28
K0+450 | 8 | 7 | 16 | 14 |  | K2+275 | 30 | 16 | 60 | 32
K0+500 | 8 | 8 | 16 | 16 |  | K2+325 | 30 | 20 | 60 | 40
K0+550 | 11 | 11 | 22 | 22 |  | K2+375 | 7 | 11 | 14 | 22
K0+600 | 7 | 19 | 14 | 38 |  | K2+425 | 28 | 28 | 56 | 56
K0+650 | 18 | 13 | 36 | 26 |  | K2+475 | 28 | 10 | 56 | 20
K0+700 | 24 | 10 | 48 | 20 |  | K2+525 | 17 | 20 | 34 | 40
K0+750 | 10 | 13 | 20 | 26 |  | K2+575 | 13 | 17 | 26 | 34
K0+800 | 0 | 18 | 0 | 36 |  | K2+625 | 30 | 18 | 60 | 36
K0+850 | 20 | 3 | 40 | 6 |  | K2+675 | 13 | 18 | 26 | 36
K0+900 | 20 | 15 | 40 | 30 |  | K2+725 | 23 | 23 | 46 | 46
K0+950 | 25 | 11 | 50 | 22 |  | K2+775 | 30 | 30 | 60 | 60
K1+000 | 3 | 2 | 6 | 4 |  | K2+825 | 28 | 27 | 56 | 54
K1+050 | 8 | 3 | 16 | 6 |  | K2+875 | 17 | 20 | 34 | 40
K1+100 | 15 | 15 | 30 | 30 |  | K2+925 | 25 | 20 | 50 | 40
K1+150 | 5 | 10 | 10 | 20
K1+200 | 13 | 18 | 26 | 36
K1+250 | 10 | 16 | 20 | 32
K1+300 | 15 | 10 | 30 | 20
K1+350 | 20 | 16 | 40 | 32
K1+400 | 3 | 10 | 6 | 20
K1+450 | 25 | 15 | 50 | 30
K1+500 | 25 | 18 | 50 | 36
K1+550 | 5 | 5 | 10 | 10
L | 31.7222 | S | 14.4907 | Za | 2 | Lr=L+ZaS | 60.7036 |  | Actual Score | 100
Technical Supervisor: Quality Inspector: Recorder: